## Slide 1: EEE MSc Project Guidance notes
Part 2/6

## Slide 2: Content
Need for project and time management
Time management
Setting aims and objectives
Project management cycle
Milestones and deliverables
Gantt chart
Final thoughts

## Slide 3: The need – project management
Science/eng. is difficult to predict (e.g. “A significant discovery will be made in 15 months and 5 days time”)
Good planning gives framework from which to work and monitor progress
Goals/plans encourage achievement in set time
Usually an obvious aim (test hypothesis, build prototype etc).
Estimate what/when needs to be done.
Unexpected breakthroughs – alter timeline/emphasis accordingly.
Notes: Goals/plans encourage achievement within a set timeframe, whilst allowing for fact that research can be vague and unpredictable.

## Slide 4: The need – time management
Poor time management (not lack of time) → unfulfilled objectives
Log all activities (daily, weekly), analyze time commitment and where time wasted on low priority activities
Note productivity rhythm - peaks and dips in energy (morning person or night owl?) – know when to take a break/change task.
  e.g. morning person – lab work am, routine work (literature searching/writing notes) pm
Write to-do lists
Notes: 24 hours a day, up to you how best to use them!
Fine tune our working practices and daily schedule to maximise chance of project success.
  To-do lists are essential if you have a number of different tasks to do, different sorts of tasks or a number of commitments to take care of simultaneously. Difficult to juggle in your head. Crossing off accomplished tasks relieves stress of demands on your time that make you feel out of control/overburdened. If you don’t write it down you might forget it, or remember it at the wrong time (ie. after the event)

## Slide 5: Time management
Get organised!
Write a to-do list (breakdown large tasks into components)
  essential if large no. of tasks or commitments, different sorts of tasks)
  Cross off accomplished tasks as achieved
Prioritise (A, B, C) and work through tiered task list in priority order (daily, weekly tasks)
Multi-tasking?
  Less efficient at any one task
  Increase stress levels/reduce productivity

## Slide 6: Time management
Pareto principle:
  80% of tasks completed in 20% of time.
  Remaining 20% takes 80% of time.
  Identify the 20% that → 80% of results key to effective use of time.
Spending time unsuccessfully
Activities taking longer than expected
Little output compared to effort made
Working on activities advancing overall goals
Seeking help where necessary
Feel sense of achievement
May not like task but see bigger picture
Effective 20%
Unproductive 80%
Notes: Pareto analysis – relation between input and output of work not proportional.
Therefore higher priority for first 80%.
Such analysis provides increased awareness of the way you work and time you spend on a variety of activities – helps you learn to focus on what is essential and helps reduce time spent on unproductive tasks.

## Slide 7: Setting project aims and objectives
Create an action plan:
  Clarify aims and objectives -
    Write down long term project goals/objectives
    Break down project into manageable steps – reasonable and realistic goals (month, week)
    How will you know when you’ve achieved your goal?
  List of actions - what to do to achieve goals. Any limitations/constraints?
  Prioritise list so most efficient first (help achieve goals).
  Organise actions into a plan (actions in a time frame)
  Monitor and measure progress (make adjustments)
Notes: Clarify aims – this is your statement of intent. What do you want to achieve? What is your goal?
Clarify objectives – these are more specific outcomes that will help in achieving your aims.
Organise actions into a plan (actions in a time frame) – can you do the actions you’ve set up for yourself in the timeframe you have allocated? How will you monitor and measure your progress against these actions, and make any necessary adjustments to the plan…..> SMART objectives!

## Slide 8: SMART objectives
Specific
Measurable
Attainable
Realistic
Time-related
→ Plan = how you will achieve your SMART objectives.
Notes: Objectives need to be SMART – i.e. no point setting a goal that you cannot measure, attain, or isn’t realistic. e.g. if not physically fit, running a marathon next week is specific and measurable, but isn’t attainable or realistic in the timeframe you’ve allowed yourself.
Your plan (and project management) is then about how you will achieve your objectives.

## Slide 9: Project management
Don’t overly complicate task list and interdependencies
Need a cushion in case of disaster (snow, component failure, delivery time)
Include regular planning and evaluation sessions (supervisor) - Update/edit plan.
Keep eye on long term goals (even if following short term pattern), remain flexible. e.g.
Literature review
Task h
Start literature review
Task i
Task j
Task k
Notes: Over-complication adds time in management.
Even a small problem can blow up bigger if no time is allowed for correction.
Update/edit plan – make sure time slots are still feasible. You might have to cut tasks accordingly. Weeds out inefficiency, problematic tasks, and ensures you are heading on track.

## Slide 10: Project management
Planning, organisation, managing resources to achieve successful completion of project objectives within project constraints (scope, time, budget)
Use Gantt chart – bar chart illustrating project schedule (start, finish, interdependencies of tasks).
Used in all research projects (requirement for grant proposals)
Project management software (e.g. MS Project) or Excel OK here.

## Slide 11: Project management
Project cycle:
Identify deliverables (outputs) and create work breakdown structure (WBS)
Identify activities needed to complete these deliverables (resource requirements, time, cost)
Develop schedule (+budget)
Risk planning
Initiation
Planning/design
Execution
Monitor/control
Notes: Initiation: Determine scope of the project and general aims and goals or requirements.
WBS – start with end objective and subdivide into manageable components in size and duration including all necessary steps to achieve objective.

## Slide 12: Project management
Project cycle:
Measure ongoing project activities
Where we are (measurement),
Where we should be (evaluation),
How to get back on track (correction)?
Initiation
Planning/design
Execution
Monitor/control
Notes: Monitor/control usually occurs during supervisor sessions

## Slide 13: Milestones and deliverables
Achievable short term goals focus effort and structure work
Displayed within Gantt chart
Deliverable:
  Project result delivered to customer at the end of a project task (e.g. prototype, feasibility study, subset of experiments/simulations)
  Tangible and verifiable
Milestone:
  Significant end point of a distinct stage
  Not tangible, perhaps a decision point or short report
  Internal project result used to check progress
  Some deliverables will be key events → milestone
Notes: Gantt chart is the typical tool for communicating project schedule status.
Deliverables usually milestones but milestones not always deliverables.
Need a balance of milestones and deliverables. Don’t make every deliverable a milestone. Milestones must be adhered to – these are major reflection points in the project.

## Slide 14: Typical MSc project Gantt chart
Task name | wk 1 | wk 2 | wk 3 | wk 4 | wk 5 | wk 6 | wk 7 | wk 8 | wk 9 | wk 10 | wk 11 | wk 12
Task 1 |  |  |  |  |  |  |  |  |  |  |  | 
Task 2 |  |  |  |  |  |  |  |  |  |  |  | 
Task 3 |  |  |  |  |  |  |  |  |  |  |  | 
Task 4 |  |  |  |  |  |  |  |  |  |  |  | 
Task 5 |  |  |  |  |  |  |  |  |  |  |  | 
Task 6 |  |  |  |  |  |  |  |  |  |  |  | 
Write-up |  |  |  |  |  |  |  |  |  |  |  | 
D1
D2
D3
There may be interdependencies from one task to another
Deliverable could be something that needs to be completed before moving to next stage
Requires explanation (200 word in Interim report)
Baseline duration
Slack
Notes: Easy to understand visual representation of project.
Add actual and revised time estimates to the Gantt chart gives a quick overview of project status when reporting…..

## Slide 15
Task name | wk 1 | wk 2 | wk 3 | wk 4 | wk 5 | wk 6 | wk 7 | wk 8 | wk 9 | wk 10 | wk 11 | wk 12
Task 1 |  |  |  |  |  |  |  |  |  |  |  | 
Task 2 |  |  |  |  |  |  |  |  |  |  |  | 
Task 3 |  |  |  |  |  |  |  |  |  |  |  | 
Task 4 |  |  |  |  |  |  |  |  |  |  |  | 
Task 5 |  |  |  |  |  |  |  |  |  |  |  | 
Task 6 |  |  |  |  |  |  |  |  |  |  |  | 
Write-up |  |  |  |  |  |  |  |  |  |  |  | 
D1
D2
D3
Baseline duration
slack
Actual completed
Remaining duration
Notes: Either activity is complete and actual is known, or new information suggests the estimate of time be revised and reflected in status report.
Note in this example that at 6 week meeting task 3 completed early, so started task 4 and 5 early. However, task 4 has met with delays. Result is that write up only attributed 1 week now, and given more slack for task 5 as task 4 the problem.

## Slide 16: Risk
Impact on cost, schedule, quality
Malfunction, change in technical requirements
Can be
  anticipated (e.g. slippage)
  beyond anticipation (breakage)
Recognise and manage potential and unforeseen trouble spots.
List risks, chances of events occurring, when they may occur, contingency plans for each risk event.
Notes: Identify as many risk events as possible to minimise their impact. Manage responses to these events.
Risk events in latter stages of project more difficult to respond to than in early stages when you can work around risk.

## Slide 17: Risk event
Cost
Time
Risk

## Slide 18: Risk Management
Risk ID – identify sources of risk
Risk assessment – severity, likelihood, controllability
Risk response – how to reduce possible damage, contingency plans
Risk response control – implement risk strategy, monitor/adjust plan

## Slide 19: Risk ID
Design – does design depend on unrealistic or optimistic assumptions?
Testing – will testing equipment be available when needed?
Schedule – is schedule dependent on completion of other tasks?
Development – is development process supported by a set of procedures, methods, tools?

## Slide 20: Risk assessment
  Scenario analysis - evaluate (tabulate) for each task on a scale of 1 to 5.
  Probability of event
  Impact of event
  Detection
  When?
  FMEA – Failure mode and effects analysis
  Impact x probability x detection = Risk value
Notes: Detection 1 = a chimpanzee could detect it, 5 = very hard to detect is failure is coming.
Don’t live by this method though as impact 1 but detection 5 gives same risk as impact 5 detection 1. Need a thoughtful analysis.

## Slide 21: Risk mitigation
Reduce likelihood that event will occur.
This is preventative (e.g. multiple methods, multiple suppliers/sources etc)
2) Reduce impact that event would have on project.
This is limiting damage or finding a new route to objectives once risk event occurs.

## Slide 22: Final thoughts
Supervisor
  will give scientific/technical guidance, advice on planning, read/comment on work
  will not tell you exactly what to do, exactly what to read, micro-manage your project
Include write-up time in Gantt chart
  but how long?
  base it on how long it takes interim report write up and scale accordingly
  Good scientific writing / good figures take a long time
  Useful to factor in feedback